## FRICTION_DATA
request_id | request_type | from_team | to_team | submitted_datetime | completed_datetime | status | sla_hours | age_hours | sla_breached | handoff_count | priority
RQ-101 | Data | Infrastructure | Client Ops | 2026-01-09 06:13 |  | Waiting | 4 | 13.7833 | TRUE | 1 | High
RQ-102 | Change | Data Platform | Reporting/BI | 2026-01-09 03:53 | 2026-01-09 10:41 | Completed | 4 | 6.8076 | TRUE | 2 | High
RQ-103 | Approval | Reporting/BI | Client Ops | 2026-01-08 10:23 |  | Waiting | 8 | 33.6167 | TRUE | 1 | High
RQ-104 | Finance | Full Stack Dev | Infrastructure | 2026-01-08 15:37 | 2026-01-08 20:40 | Completed | 48 | 5.0493 | FALSE | 1 | Normal
RQ-105 | Finance | Full Stack Dev | Finance Ops | 2026-01-08 09:35 | 2026-01-08 19:36 | Completed | 48 | 10.016 | FALSE | 2 | Normal
RQ-106 | Access | Integration | Data Platform | 2026-01-09 03:29 | 2026-01-09 23:37 | Completed | 12 | 20.1354 | TRUE | 1 | High
RQ-107 | Approval | QA/UAT | Security | 2026-01-08 20:42 | 2026-01-10 12:07 | Completed | 4 | 39.4099 | TRUE | 2 | High
RQ-108 | Change | Security | Integration | 2026-01-09 07:13 | 2026-01-09 21:40 | Completed | 48 | 14.4469 | FALSE | 3 | Normal
RQ-109 | Change | Client Ops | HR Ops | 2026-01-08 18:13 | 2026-01-09 02:20 | Completed | 8 | 8.1091 | TRUE | 2 | High
RQ-110 | Access | Data Platform | HR Ops | 2026-01-09 01:55 | 2026-01-09 16:51 | Completed | 24 | 14.9402 | FALSE | 3 | Normal
RQ-111 | Data | QA/UAT | Data Platform | 2026-01-08 12:01 | 2026-01-08 23:00 | Completed | 48 | 10.9906 | FALSE | 3 | Normal
RQ-112 | Access | Client Ops | Reporting/BI | 2026-01-08 09:20 | 2026-01-09 14:21 | Completed | 4 | 29.0101 | TRUE | 1 | High
RQ-113 | Snowflake Role | HR Ops | Reporting/BI | 2026-01-09 07:43 | 2026-01-09 18:58 | Completed | 12 | 11.2437 | FALSE | 1 | Medium
RQ-114 | Finance | Data Platform | Infrastructure | 2026-01-08 17:12 | 2026-01-11 02:51 | Completed | 24 | 57.6525 | TRUE | 2 | High
RQ-115 | SFTP Move | Finance Ops | Integration | 2026-01-08 17:42 | 2026-01-08 20:09 | Completed | 24 | 2.4465 | FALSE | 2 | Normal
RQ-116 | Finance | HR Ops | Infrastructure | 2026-01-09 04:51 | 2026-01-10 01:23 | Completed | 4 | 20.53 | TRUE | 1 | High
RQ-117 | Data | Infrastructure | Finance Ops | 2026-01-08 21:34 | 2026-01-09 04:41 | Completed | 24 | 7.1085 | FALSE | 2 | Normal
RQ-118 | Access | Client Ops | Reporting/BI | 2026-01-09 02:45 | 2026-01-09 04:38 | Completed | 12 | 1.8882 | FALSE | 2 | Normal
RQ-119 | Snowflake Role | Integration | Finance Ops | 2026-01-08 22:10 | 2026-01-09 12:55 | Completed | 12 | 14.7472 | TRUE | 2 | High
RQ-120 | Access | Infrastructure | Data Platform | 2026-01-08 14:00 |  | Waiting | 8 | 30 | TRUE | 1 | High
RQ-121 | Access | Full Stack Dev | Integration | 2026-01-09 04:06 |  | Waiting | 8 | 15.9 | TRUE | 1 | High
RQ-122 | Approval | Infrastructure | Client Ops | 2026-01-09 02:14 | 2026-01-09 05:30 | Completed | 12 | 3.2718 | FALSE | 3 | Normal
RQ-123 | Access | Integration | Full Stack Dev | 2026-01-08 23:35 | 2026-01-10 01:43 | Completed | 48 | 26.137 | FALSE | 2 | Normal
RQ-124 | Approval | Client Ops | Reporting/BI | 2026-01-08 10:07 |  | Waiting | 8 | 33.8833 | TRUE | 2 | High
RQ-125 | Access | Client Ops | Infrastructure | 2026-01-08 11:45 | 2026-01-11 05:47 | Completed | 12 | 66.0282 | TRUE | 3 | High
RQ-126 | Access | Integration | Data Platform | 2026-01-08 20:24 |  | Waiting | 48 | 23.6 | FALSE | 1 | Normal
RQ-127 | Snowflake Role | Security | Client Ops | 2026-01-08 13:04 | 2026-01-08 21:44 | Completed | 12 | 8.6696 | FALSE | 3 | Medium
RQ-128 | Finance | Data Platform | Infrastructure | 2026-01-09 00:39 | 2026-01-09 02:24 | Completed | 24 | 1.7459 | FALSE | 1 | Normal
RQ-129 | Access | Data Platform | Reporting/BI | 2026-01-08 17:02 | 2026-01-08 18:34 | Completed | 24 | 1.5265 | FALSE | 3 | Normal
RQ-130 | Approval | Security | QA/UAT | 2026-01-08 20:20 | 2026-01-09 08:34 | Completed | 8 | 12.2354 | TRUE | 3 | High
RQ-131 | Snowflake Role | Integration | Finance Ops | 2026-01-09 05:56 | 2026-01-09 12:24 | Completed | 4 | 6.462 | TRUE | 2 | High
RQ-132 | Data | Infrastructure | Reporting/BI | 2026-01-08 15:36 | 2026-01-09 02:24 | Completed | 48 | 10.8065 | FALSE | 2 | Normal
RQ-133 | SFTP Move | Security | Finance Ops | 2026-01-08 16:10 | 2026-01-09 04:15 | Completed | 24 | 12.0868 | FALSE | 2 | Normal
RQ-134 | Change | Client Ops | HR Ops | 2026-01-08 08:59 | 2026-01-08 11:29 | Completed | 4 | 2.4945 | FALSE | 2 | Normal
RQ-135 | Access | QA/UAT | HR Ops | 2026-01-08 23:15 | 2026-01-09 13:40 | Completed | 12 | 14.4105 | TRUE | 2 | High
RQ-136 | Access | Data Platform | Finance Ops | 2026-01-09 00:02 | 2026-01-09 09:19 | Completed | 8 | 9.2837 | TRUE | 3 | High
RQ-137 | Change | Full Stack Dev | Integration | 2026-01-09 06:17 | 2026-01-12 04:40 | Completed | 12 | 70.3808 | TRUE | 1 | High
RQ-138 | Approval | Reporting/BI | Security | 2026-01-09 00:19 | 2026-01-09 07:43 | Completed | 8 | 7.4066 | FALSE | 1 | Medium
RQ-139 | Approval | Reporting/BI | Integration | 2026-01-08 21:42 | 2026-01-08 23:01 | Completed | 4 | 1.3092 | FALSE | 2 | Normal
RQ-140 | Access | Full Stack Dev | Security | 2026-01-09 04:09 | 2026-01-09 11:28 | Completed | 24 | 7.3143 | FALSE | 2 | Normal
RQ-141 | Snowflake Role | QA/UAT | Client Ops | 2026-01-09 06:26 |  | Waiting | 12 | 13.5667 | TRUE | 3 | High
RQ-142 | Change | Infrastructure | Full Stack Dev | 2026-01-08 08:29 | 2026-01-08 13:03 | Completed | 4 | 4.5696 | TRUE | 2 | High
RQ-143 | Finance | Security | Finance Ops | 2026-01-08 08:57 |  | Waiting | 12 | 35.05 | TRUE | 2 | High
RQ-144 | Change | Security | Reporting/BI | 2026-01-08 16:51 | 2026-01-09 00:42 | Completed | 48 | 7.8503 | FALSE | 3 | Normal
RQ-145 | SFTP Move | HR Ops | Integration | 2026-01-09 06:36 | 2026-01-09 09:58 | Completed | 48 | 3.3618 | FALSE | 1 | Normal
RQ-146 | Snowflake Role | Integration | Infrastructure | 2026-01-09 02:09 | 2026-01-11 01:01 | Completed | 8 | 46.8654 | TRUE | 2 | High
RQ-147 | Snowflake Role | Infrastructure | Full Stack Dev | 2026-01-08 13:06 |  | Waiting | 8 | 30.9 | TRUE | 3 | High
RQ-148 | Change | Data Platform | QA/UAT | 2026-01-08 10:06 | 2026-01-09 11:53 | Completed | 12 | 25.7897 | TRUE | 3 | High
RQ-149 | Finance | Data Platform | QA/UAT | 2026-01-08 09:56 |  | Waiting | 8 | 34.0667 | TRUE | 3 | High
RQ-150 | Approval | Data Platform | QA/UAT | 2026-01-08 23:26 |  | Waiting | 48 | 20.5667 | FALSE | 1 | Normal
RQ-151 | Approval | Client Ops | HR Ops | 2026-01-09 04:54 | 2026-01-09 17:42 | Completed | 48 | 12.7982 | FALSE | 3 | Normal
RQ-152 | Data | Client Ops | QA/UAT | 2026-01-09 02:12 | 2026-01-09 19:03 | Completed | 24 | 16.8424 | FALSE | 1 | Medium
RQ-153 | Change | Finance Ops | QA/UAT | 2026-01-08 14:54 |  | Waiting | 24 | 29.1 | TRUE | 1 | High
RQ-154 | Approval | Reporting/BI | Integration | 2026-01-08 18:47 | 2026-01-09 03:22 | Completed | 4 | 8.5793 | TRUE | 2 | High
RQ-155 | Access | Finance Ops | Data Platform | 2026-01-08 13:16 |  | Waiting | 12 | 30.7333 | TRUE | 1 | High
RQ-156 | Access | Client Ops | Security | 2026-01-08 11:12 | 2026-01-08 12:47 | Completed | 24 | 1.5827 | FALSE | 2 | Normal
RQ-157 | SFTP Move | Security | Infrastructure | 2026-01-08 22:43 | 2026-01-09 12:18 | Completed | 48 | 13.5761 | FALSE | 1 | Normal
RQ-158 | Data | HR Ops | Data Platform | 2026-01-08 20:29 | 2026-01-09 00:54 | Completed | 4 | 4.4165 | TRUE | 3 | High
RQ-159 | SFTP Move | Full Stack Dev | Client Ops | 2026-01-08 19:18 | 2026-01-09 03:09 | Completed | 48 | 7.8535 | FALSE | 3 | Normal
RQ-160 | Approval | Data Platform | Finance Ops | 2026-01-08 11:34 |  | Waiting | 4 | 32.4333 | TRUE | 3 | High

## OWNERSHIP_REGISTRY
asset_type | asset_name | owner_team | contact_channel | manager_email | runbook_link
Snowflake | PROD_SALES.CURATED.ORDERS | Data Platform | #data-platform | data.manager@brown.example | https://intranet.brown.example/runbooks/data-platform
Snowflake | PROD_SALES.CURATED.CUSTOMERS | Reporting/BI | #reporting-bi | reporting/bi.manager@brown.example | https://intranet.brown.example/runbooks/reporting/bi
Snowflake | PROD_SALES.RAW.SALESFORCE_OPPORTUNITIES | Finance Ops | #finance-ops | finance.manager@brown.example | https://intranet.brown.example/runbooks/finance-ops
Snowflake | PROD_FIN.CURATED.GENERAL_LEDGER | Reporting/BI | #reporting-bi | reporting/bi.manager@brown.example | https://intranet.brown.example/runbooks/reporting/bi
Snowflake | PROD_FIN.CURATED.EXPENSES | Client Ops | #client-ops | client.manager@brown.example | https://intranet.brown.example/runbooks/client-ops
Snowflake | PROD_HR.CURATED.EMPLOYEE_DIM | Finance Ops | #finance-ops | finance.manager@brown.example | https://intranet.brown.example/runbooks/finance-ops
Snowflake | PROD_RPT.PUBLISH.MONTHLY_PERFORMANCE | Client Ops | #client-ops | client.manager@brown.example | https://intranet.brown.example/runbooks/client-ops
Snowflake | PROD_RISK.CURATED.KYC_ALERTS | Reporting/BI | #reporting-bi | reporting/bi.manager@brown.example | https://intranet.brown.example/runbooks/reporting/bi
Snowflake | PROD_MKT.CURATED.CAMPAIGN_ATTRIBUTION | Integration | #integration | integration.manager@brown.example | https://intranet.brown.example/runbooks/integration
Snowflake | PROD_OPS.CURATED.SFTP_AUDIT_LOGS | Integration | #integration | integration.manager@brown.example | https://intranet.brown.example/runbooks/integration
SFTP | /sftp/inbound/fullstack/requests/ | Data Platform | #data-platform | data.manager@brown.example | https://intranet.brown.example/runbooks/data-platform
SFTP | /sftp/inbound/finance/vendor_files/ | Client Ops | #client-ops | client.manager@brown.example | https://intranet.brown.example/runbooks/client-ops
SFTP | /sftp/outbound/clientops/reports/ | Data Platform | #data-platform | data.manager@brown.example | https://intranet.brown.example/runbooks/data-platform
SFTP | /sftp/outbound/integration/partners/ | Client Ops | #client-ops | client.manager@brown.example | https://intranet.brown.example/runbooks/client-ops
SFTP | /sftp/inbound/dataplatform/raw_drop/ | Integration | #integration | integration.manager@brown.example | https://intranet.brown.example/runbooks/integration
Application | Access Request Portal | Full Stack Dev | #full-stack-dev | full.manager@brown.example | https://intranet.brown.example/runbooks/full-stack-dev
Application | Release Change Calendar | Infrastructure | #infrastructure | infrastructure.manager@brown.example | https://intranet.brown.example/runbooks/infrastructure
Application | Client Reporting Hub | Security | #security | security.manager@brown.example | https://intranet.brown.example/runbooks/security
Application | Identity & SSO Admin | Client Ops | #client-ops | client.manager@brown.example | https://intranet.brown.example/runbooks/client-ops
Application | Vendor File Exchange Console | Infrastructure | #infrastructure | infrastructure.manager@brown.example | https://intranet.brown.example/runbooks/infrastructure

## ESCALATION_LOG
timestamp | request_id | reason | escalated_to | channel_posted | status

## INCIDENTS
incident_id | title | incident_type | severity | status | created_at | updated_at | asset_type | asset_name | owner_team | contact_channel | blocked_reason | description
INC-2001 | Dashboard Stale: Client Reporting Hub | Dashboard Stale | Sev3 | Blocked | 2026-01-06 20:32 | 2026-01-07 13:26 | Application | Client Reporting Hub |  |  | Missing access | Users reporting issue related to Application asset 'Client Reporting Hub'. Needs routing to the right owner.
INC-2002 | Permission Error: | Permission Error | Sev3 | Open | 2026-01-06 22:41 | 2026-01-07 02:46 | SFTP | /sftp/outbound/integration/partners/ | Client Ops | #client-ops |  | Users reporting issue related to SFTP asset '/sftp/outbound/integration/partners/'. Needs routing to the right owner.
INC-2003 | Permission Error: Release Change Calendar | Permission Error | Sev3 | Investigating | 2026-01-07 05:32 | 2026-01-08 02:19 | Application | Release Change Calendar | Infrastructure | #infrastructure |  | Users reporting issue related to Application asset 'Release Change Calendar'. Needs routing to the right owner.
INC-2004 | Job Timeout: SFTP_AUDIT_LOGS | Job Timeout | Sev1 | Investigating | 2026-01-09 00:58 | 2026-01-09 07:54 | Snowflake | PROD_OPS.CURATED.SFTP_AUDIT_LOGS | Integration | #integration |  | Users reporting issue related to Snowflake asset 'PROD_OPS.CURATED.SFTP_AUDIT_LOGS'. Needs routing to the right owner.
INC-2005 | Dashboard Stale: EXPENSES | Dashboard Stale | Sev2 | Investigating | 2026-01-08 06:27 | 2026-01-08 14:07 | Snowflake | PROD_FIN.CURATED.EXPENSES | Client Ops | #client-ops |  | Users reporting issue related to Snowflake asset 'PROD_FIN.CURATED.EXPENSES'. Needs routing to the right owner.
INC-2006 | Permission Error: Identity & SSO Admin | Permission Error | Sev1 | Investigating | 2026-01-07 03:25 | 2026-01-07 06:10 | Application | Identity & SSO Admin | Client Ops | #client-ops |  | Users reporting issue related to Application asset 'Identity & SSO Admin'. Needs routing to the right owner.
INC-2007 | SFTP Transfer Failure: EXPENSES | SFTP Transfer Failure | Sev3 | Open | 2026-01-08 18:35 | 2026-01-08 22:29 | Snowflake | PROD_FIN.CURATED.EXPENSES | Client Ops | #client-ops |  | Users reporting issue related to Snowflake asset 'PROD_FIN.CURATED.EXPENSES'. Needs routing to the right owner.
INC-2008 | Data Pipeline Failure: CAMPAIGN_ATTRIBUTION | Data Pipeline Failure | Sev3 | Open | 2026-01-08 05:01 | 2026-01-08 06:31 | Snowflake | PROD_MKT.CURATED.CAMPAIGN_ATTRIBUTION | Integration | #integration |  | Users reporting issue related to Snowflake asset 'PROD_MKT.CURATED.CAMPAIGN_ATTRIBUTION'. Needs routing to the right owner.
INC-2009 | Dashboard Stale: | Dashboard Stale | Sev2 | Investigating | 2026-01-08 06:11 | 2026-01-09 03:28 | SFTP | /sftp/inbound/finance/vendor_files/ |  |  |  | Users reporting issue related to SFTP asset '/sftp/inbound/finance/vendor_files/'. Needs routing to the right owner.
INC-2010 | Snowflake Access Issue: MONTHLY_PERFORMANCE | Snowflake Access Issue | Sev1 | Open | 2026-01-08 16:52 | 2026-01-09 00:37 | Snowflake | PROD_RPT.PUBLISH.MONTHLY_PERFORMANCE |  |  |  | Users reporting issue related to Snowflake asset 'PROD_RPT.PUBLISH.MONTHLY_PERFORMANCE'. Needs routing to the right owner.
INC-2011 | Dashboard Stale: Access Request Portal | Dashboard Stale | Sev3 | Open | 2026-01-06 08:48 | 2026-01-06 23:20 | Application | Access Request Portal | Full Stack Dev | #full-stack-dev |  | Users reporting issue related to Application asset 'Access Request Portal'. Needs routing to the right owner.
INC-2012 | SFTP Transfer Failure: Identity & SSO Admin | SFTP Transfer Failure | Sev2 | Open | 2026-01-07 05:34 | 2026-01-07 11:34 | Application | Identity & SSO Admin | Client Ops | #client-ops |  | Users reporting issue related to Application asset 'Identity & SSO Admin'. Needs routing to the right owner.
INC-2013 | Job Timeout: Release Change Calendar | Job Timeout | Sev2 | Blocked | 2026-01-08 05:49 | 2026-01-08 18:43 | Application | Release Change Calendar | Infrastructure | #infrastructure | Unknown owner | Users reporting issue related to Application asset 'Release Change Calendar'. Needs routing to the right owner.
INC-2014 | Data Pipeline Failure: | Data Pipeline Failure | Sev3 | Open | 2026-01-07 23:00 | 2026-01-08 23:39 | SFTP | /sftp/inbound/finance/vendor_files/ | Client Ops | #client-ops |  | Users reporting issue related to SFTP asset '/sftp/inbound/finance/vendor_files/'. Needs routing to the right owner.
INC-2015 | Dashboard Stale: ORDERS | Dashboard Stale | Sev1 | Open | 2026-01-08 01:00 | 2026-01-08 20:23 | Snowflake | PROD_SALES.CURATED.ORDERS | Data Platform | #data-platform |  | Users reporting issue related to Snowflake asset 'PROD_SALES.CURATED.ORDERS'. Needs routing to the right owner.
INC-2016 | SFTP Transfer Failure: | SFTP Transfer Failure | Sev3 | Investigating | 2026-01-08 14:05 | 2026-01-09 02:16 | SFTP | /sftp/inbound/dataplatform/raw_drop/ | Integration | #integration |  | Users reporting issue related to SFTP asset '/sftp/inbound/dataplatform/raw_drop/'. Needs routing to the right owner.
INC-2017 | SFTP Transfer Failure: | SFTP Transfer Failure | Sev3 | Open | 2026-01-08 07:50 | 2026-01-09 07:30 | SFTP | /sftp/outbound/integration/partners/ |  |  |  | Users reporting issue related to SFTP asset '/sftp/outbound/integration/partners/'. Needs routing to the right owner.
INC-2018 | Dashboard Stale: EMPLOYEE_DIM | Dashboard Stale | Sev3 | Investigating | 2026-01-07 02:57 | 2026-01-07 06:03 | Snowflake | PROD_HR.CURATED.EMPLOYEE_DIM | Finance Ops | #finance-ops |  | Users reporting issue related to Snowflake asset 'PROD_HR.CURATED.EMPLOYEE_DIM'. Needs routing to the right owner.
INC-2019 | Snowflake Access Issue: EXPENSES | Snowflake Access Issue | Sev2 | Blocked | 2026-01-07 23:34 | 2026-01-08 19:05 | Snowflake | PROD_FIN.CURATED.EXPENSES | Client Ops | #client-ops | Unknown owner | Users reporting issue related to Snowflake asset 'PROD_FIN.CURATED.EXPENSES'. Needs routing to the right owner.
INC-2020 | SFTP Transfer Failure: Access Request Portal | SFTP Transfer Failure | Sev2 | Investigating | 2026-01-08 22:43 | 2026-01-09 05:41 | Application | Access Request Portal | Full Stack Dev | #full-stack-dev |  | Users reporting issue related to Application asset 'Access Request Portal'. Needs routing to the right owner.
INC-2021 | Data Pipeline Failure: ORDERS | Data Pipeline Failure | Sev2 | Open | 2026-01-09 00:58 | 2026-01-09 06:16 | Snowflake | PROD_SALES.CURATED.ORDERS | Data Platform | #data-platform |  | Users reporting issue related to Snowflake asset 'PROD_SALES.CURATED.ORDERS'. Needs routing to the right owner.
INC-2022 | SFTP Transfer Failure: | SFTP Transfer Failure | Sev1 | Open | 2026-01-06 22:39 | 2026-01-07 20:25 | SFTP | /sftp/outbound/clientops/reports/ | Data Platform | #data-platform |  | Users reporting issue related to SFTP asset '/sftp/outbound/clientops/reports/'. Needs routing to the right owner.
INC-2023 | SFTP Transfer Failure: EXPENSES | SFTP Transfer Failure | Sev3 | Resolved | 2026-01-06 19:02 | 2026-01-07 06:46 | Snowflake | PROD_FIN.CURATED.EXPENSES | Client Ops | #client-ops |  | Users reporting issue related to Snowflake asset 'PROD_FIN.CURATED.EXPENSES'. Needs routing to the right owner.
INC-2024 | Data Pipeline Failure: | Data Pipeline Failure | Sev3 | Open | 2026-01-08 23:14 | 2026-01-09 08:34 | SFTP | /sftp/inbound/dataplatform/raw_drop/ | Integration | #integration |  | Users reporting issue related to SFTP asset '/sftp/inbound/dataplatform/raw_drop/'. Needs routing to the right owner.
INC-2025 | Data Pipeline Failure: | Data Pipeline Failure | Sev2 | Open | 2026-01-09 02:03 | 2026-01-10 01:50 | SFTP | /sftp/inbound/dataplatform/raw_drop/ | Integration | #integration |  | Users reporting issue related to SFTP asset '/sftp/inbound/dataplatform/raw_drop/'. Needs routing to the right owner.

## ACTION_LOG
timestamp | incident_id | action | actor | details